Závěrečná zpráva o řešení projektu

AKTION 55p4

Erozní a transportní procesy – experimentální a simulační metody výzkumu

(Soil erosion and transport processes – experimental and simulation methods).

za rok 2009

(vyúčtování za českou stranu)

Česká strana:

Katedra Hydromeliorací a krajinného inženýrství

Fakulta Stavební

ČVUT v Praze

zodpovědná osoba: Tomáš Dostál doc.Ing., Dr.

Rakouská strana:

Department of Water, Atmosphere and Environment,

Institute of Hydraulics and Rural Water Management

University of Agricultural Sciences (BOKU) Wien

zodpovědná osoba: Andreas Klik Prof., Dipl.Ing. Dr.

Náplní projektu na rok 2009 byla jednak vzájemná návštěva spolupracujících týmů za účelem koordinace společně probíhajícího výzkumu a přípravy společných intenzivních výukových kurzů pro studenty obou univerzit a především intenzivní společné výukové kurzy pro studenty v délce trvání po 1 týdnu v Praze (ČVUT v Praze) a ve Vídni (BOKU Wien). V rámci návštěv zaměstnanců bylo diskutováno mimo jiné společné zapojení obou pracovišť do projektu v rámci 7. rámcového programu, byly hledány další možnosti organizování společných akcí a hledány zdroje pro financování společných terénních měření a experimentálních kampaní.

V rámci projektu byly realizovány oba plánované intenzivní výukové kurzy v plánované délce, ale s mírnými úpravami v termínech. Co se týče vzájemných návštěv členů řešitelských týmů, došlo k určitým úpravám, především v posunu termínů návštěv do podzimního období a dále v záměně cíle návštěv. Oproti původnímu plánu byla schůzka přesunuta z Prahy do Vídně. Tři pracovníci ČVUT v Praze navštívili BOKU Wien, z toho dva na celkem 3 dny a jeden na 4 dny. Ke změně došlo z důvodu časové vytíženosti členů řešitelských kolektivů. Cestovné účastníků z ČR bylo hrazeno z jiných zdrojů a pobytové náklady z ušetřených prostředků BOKU Wien.

Podrobná specifikace aktivit následuje:

I. část kurzu proběhla pod názvem „Experimental methods of soil erosion and sediment transport research“ v termínu 8. – 13.11.2009 ve Vídni s následujícím programem:

8.11.2009 – příjezd účastníků, přivítání

9.11.2009 – zahájení kurzu, všeobecné metodické přednášky a prezentace

10.11.2009 – modelování vodní eroze v laboratoři

11.11.2009 – výpočty naměřených charakteristik, statistické vyhodnocení

12.11.2009 – exkurze na terénní experimentální plochy, terénní měření, vyhodnocení dat

13.11.2009 - závěrečné shrnutí, diskuze, ukončení kurzu, odjezd účastníků

Kurzu se zúčastnilo celkem 16 studentů a 4 učitelé – z toho za českou stranu 10 studentů a 2 učitelé (doc.Dr.Ing. Tomáš Dostál a Ing. Tereza Dvořáková) a za Rakousku stranu 6 studentů a 2 učitelé (Prof. Dr. Andreas Klik a Ing. Gerlinde Trumper).

II. část kurzu se uskutečnila v termínu 29.11. – 3.12.2009 a byla organizována v Praze na Fakultě stavební ČVUT pod názvem „Simulation methods of soil erosion and sediment transport research“ s následujícím programem:

29.11.2009 - příjezd účastníků

30.11.2009 – úvodní přednášky, základy počítačového modelování

1.12.2009 – výpočet objemu sedimentu ve vodní nádrži s využitím GIS

2.12.2009 – odhad transportu sedimentu z povodí s využitím GIS

3.12.2009 – měření na laboratorním dešťovém simulátoru, vyhodnocení výsledků, závěrečná diskuze, odjezd

Kurzu se zúčastnilo celkem 25 studentů a 6 učitelů - z toho za českou stranu 10 studentů a 4 učitelé (Dr.Ing. Tomáš Dostál, Ing. Josef Krása Ph.D., Ing.Tereza Dvořáková a Ing. Pavla Schwarzová Ph.D.) a za Rakousku stranu 15 studentů a 2 učitelé (Prof. Dr. Andreas Klik a Ing. Gerlinde Trumper).

Oba kurzy na sebe navazovaly a zatímco kurz ve Vídni byl zaměřen na metody měření půdních charakteristik, kurz v Praze se zabýval využitím simulačních modelů pro posouzení erozní ohroženosti a návrh protierozních opatření. Kurz ve Vídni byl velmi kladně hodnocen jak pedagogy, tak především zúčastněnými studenty a velký zájem rakouských studentů o kurz v Praze svědčí o úspěchu této akce v loňském roce. Hodnocení kurzu několika studenty je přiloženo. Řada studentů zde získávala informace relevantní pro jejich případné následné studentské nebo doktorandské stáže a studijní pobyty. Frekventantka podobného kurzu, organizovaného v předešlém roce na podzim 2007 zpracovávala na partnerském pracovišti BOKU Wien svou diplomovou práci, kterou obhájila v lednu 2008.

Na závěr každého z kurzů studenti dostali certifikáty o absolvování s uvedením, že se jednalo o kurz, organizovaný v rámci projektu AKTION 55p4. Vzorový certifikát je rovněž přiložen. Studenti ČVUT v Praze získali za úspěšné absolvování kurzu zápočet z předmětu Ochrana a organizace povodí (K143YOOP), hodnocený dvěma kredity.

Vzájemná návštěva pracovníků účastníků projektu byla po vzájemné dohodě přesunuta z Vídně do Prahy s tím, že se jí účastnili 3 pracovníci ČVUT v Praze: doc.Ing.Dr.Tomáš Dostál v termínu 15. – 18.12.2009 a Ing.Josef Krása Ph.D. a Ing.Tereza Dvořáková v termínu 16. – 18.12.2009. Z projektu AKTION byly hrazeny pouze jejich pobytové náklady, cestovné bylo uhrazeno z jiných prostředků, díky tomu, že cesta byla spojena ještě s dalšími úkoly.

Z částky původně plánované na pokrytí cestovních nákladů českých účastníků projektu a na pokrytí pobytu Rakouských studentů a pedagogů se podařilo ušetřit část prostředků v celkové výši 17.400,- CZK,-. Tyto finance byly využity na na pokrytí nákladů souvisejících jednak s překladem studijních materiálů, které byly využity v rámci kurzu na ČVUT v Praze a budou využity i při dalších podobně zaměřených kurzech a dále pak na drobný materiál, pořízený v souvislosti s konáním kurzu.

Veškeré účtování probíhalo na pracovišti fakulty stavební ČVUT v Praze odděleně a originály účetních dokladů jsou uloženy v ekonomickém oddělení řešitelského pracoviště. I přes určité změny v organizaci projektu oproti původnímu plánu -  a dá se říci – výraznému rozšíření aktivit, byly ve všech případech dodrženy jak maximální denní limity, tak i celková částka.

Vyúčtování nákladů za českou stranu:

| Typ nákladů |  | CZK |
| --- | --- | --- |
| Úhrada ubytování rakouských partnerů v ČR | Kurz v ČR 29.11. – 3.12.2009: 15 osob, 4 noci | 28 000,- CZK |
|  | Ubytování celkem | 28 000,- CZK |
| Stravné Rakouských účastníků v ČR | Kurz v ČR - ČVUT 29.11. – 3.12.2009: Profesoři: 2x5x460,- = 4600,- CZK Studenti: 15x5x250,- = 18750,- CZK | 23 350,- CZK |
|  | Stravné celkem | 23 350,- CZK |
| Jízdné českých účastníků do Rakouska | Společná jízdenka na kurz 8. – 13.11.2009 (10+2 osoby) - vlak | 12 279,- CZK |
|  | Cestovné celkem | 12 279,- CZK |
| Materiál a služby | Drobný materiál | 9 371,- CZK |
|  | Služby - překlad | 8.000,- CZK |
|  | Materiálové náklady - celkem | 17 371,- CZK |
|  | Náklady celkem | 81 000,- CZK |

K realizaci projektu přiděleno i využito celkem: 81 000,- CZK

Zdůvodnění nákladů:

Ubytování Rakouských účastníků:

Ubytování účastníků bylo zajištěno v režijním zařízení ČVUT Masarykova kolej, kde byly přiznány režijní ceny ve výši:

Masarykova kolej:

560,- CZK/os.noc v jednolůžkovém pokoji

435,- CZK/os.noc ve dvoulůžkovém pokoji

Dva studenti BOKU Wien byli během kurzu ubytováni v Praze u svých příbuzných nebo přátel a tedy bezplatně.

Profesorům bylo zajištěno automaticky ubytování na jednolůžkových pokojích, studenti pak byli rozděleni podle kapacity převážně do dvoulůžkových pokojů.

Stravné rakouských účastníků:

Stravné pro studenty i profesory – účastníky kurzu bylo vyplaceno v plné výši 250,- Kč/os.den u studentů a 460 Kč./os.den u profesorů.

Jízdné českých účastníků do Rakouska:

Jízdné na kurz i na jednání ke konci roku bylo hrazeno fakturou za hromadnou jízdenku na vlak. Podařilo se získat maximální slevu na hromadnou jízdenku.

Doplňkové náklady:

Vzhledem k tomu, že se podařilo ušetřit část původně plánovaných nákladů, byly zbylé prostředky účelně využity k zajištění profesionálního překladu výukových materiálů, které ke kurzu vznikly a budou využívány i při jeho dalších bězích a pro pokrytí části nákladů na reprografii, tisky materiálů a prezentační techniku.

Seznam účastníků kurzu na BOKU Wien

- Milena Hlaváčová

- Jana Hejná

- Barbora Janotová

- Michaela Klímová

- Kateřina Půstová

- Miroslav Bauer

- Iva Procházková

- Petr Šmejkal

- Luděk Strouhal

- Kateřina Lišková

Profesoři:

- Doc. Tomáš Dostál

- Ing. Tereza Dvořáková

Seznam účastníků kurzu na ČVUT v Praze

- Launay Marina

- Burzle Stefan Robert

- Hufler Stefan

- Nyamdavaa Tsolomon

- Kalss Rudolf

- Kyrnychnyj Andrey

- Lassing MArco

- Lebschy Markus

- Rummele Phillip

- Mullegger Matthias Stephan

- Seidl Georg

- Selim Shady

- Staudner Margarethe

- Baatar Naran Undrakh

- Muller Georg

Profesoři:

- Prof.Andreas Klik

- Ing. Gerlinde Trumper

V Praze dne 28.1.2009

Doc.Ing.Dr.Tomáš Dostál

Final report on the project

AKTION 55p4

“Soil Erosion and sediment transport processes – experimental and simulation methods of reserach”

for 2009 year

(overview of the costs for Czech partner)

Czech partner:

Department of Drainage Irrigation and Landscape Engineering

Faculty of Civil Engineering

CTU in Prague

Tomáš Dostál Assoc.Prof.,Ing., Dr.

Austrian partner:

Department of Water, Atmosphere and Environment,

Institute of Hydraulics and Rural Water Management

University of Agricultural Sciences (BOKU) Wien

Andreas Klik Prof., Dipl.Ing. Dr.

The topic of the project for 2009 had been at first exchange visit of both teams, to coordinate ongoing research projects, cooperation and to prepare the intensive student courses with duration one week each (at CTU Prague and at BOKU Wien) and at second, intensive common student courses itselves. Further cooperation within 7th Frame Program of EU, further possibilities of joint student courses organization and funding possibilities to cover expenses of common field measurements in next years have been discussed during visits of staff in December 2007.

Within the project, both planned courses were realized in planned duration, but with small shifts in terms. Concerning of the staff visits also some partial changes had been adopted, mainly in terms of the visits and in location where they were held. In opposite to original plan, the meeting has been held in Vienna, and two staff from CTU came for three and one for 4 days. The reason of change was extreme time occupation of colleagues from BOKU. Travel expenses of Czech partners were covered from another source and allowances in Vienna were covered from budget of BOKU.

The detailed specification of the activities and costs follows:

I. part of the course had been held at BOKU Wien under the title “Experimental methods of soil erosion and sediment transport research “ during 8. – 13.11.2009 with following program:

8.11.2009 – arrival of the participants, welcome

9.11.2009 – introduction, general methodological presentations and lectures

10.11.2009 – modeling of erosion processes in soil laboratory

11.11.2009 – calculation of measured results, statistical evaluation of measured data

12.11.2009 – field trip to experimental plots, field measurements, data analysis

13.11.2009 - final discussion, conclusion, finishing of the course, departure of the participants

There were in total 16 students and 4 teachers participating at the course – from the Czech Republic 10 students and 2 teachers (Ass.Prof.Dr.Ing. Tomáš Dostál a Ing. Tereza Dvořáková) and from Austria 6 students and 2 teachers (Prof. Dr. Andreas Klik a Ing. Gerlinde Trumper).

II. part of the course at CTU in Prague under the title „ Simulation methods of soil erosion and sediment transport research“ had been held  on  29.11. – 3.12.2009 with following program:

29.11.2009 – arrival of the participants

30.11.2009 – introduction to computer modeling

1.12.2009 – sediment volume in the water reservoir assessment using GIS technology

2.12.2009 – sediment transport from the watershed assessment, using GIS technology

3.12.2009 - measurement on the laboratory rainfall simulator, results assessment, final discussion,, conclusions, finishing of the course, departure of the participants

There were in total 25 students participating at the course and 6 teachers – 10 students and 4 teachers (Assoc.Prof.Dr.Ing. Tomáš Dostál, Ing. Josef Krása Ph.D., Ing.Pavla Schwarzová Ph.D.,  and Ing.Tereza Dvořáková) from the Czech Republic and 15 students and 2 teachers from Austria (Prof. Dr. Andreas Klik, Ing. Gerlinde Trumper). The number of Austrian students has been increased, due to very high interest at BOKU to take a part at the course.

Both courses have followed each other thematically – as the course in Wien had been focused of laboratory and field measurement techniques of sol erosion processes, the Prague course was oriented more on the computer modeling and practical implementation of GIS technology. The course in Vienna had been highly appreciated by teachers, but mainly by students and high interest of the students for the Prague course had shown good image of the course organized last year. The evaluation of the course in Vienna by several CTU students is enclosed. Number of Czech students got information relevant for their further decisions about foreign stays. For instance, one participant of the course in 2006 stayed at BOKU Wien, working on her diploma thesis in fall 2007 – her thesis were worked out at rainfall simulator (the topic of the course) and were defended in January 2008.

At the end of common courses the participants obtained certificates, which approved, that students passed intensive course, held under AKTION project 55p4. The sample of the certificate is also enclosed. Students of CTU Prague gained by passing the courses assessment from course of “Watershed management” (K143YOOP), which is assessed by 2 credits.

Visit of staff has been after common agreement shifted from Prague to Vienna. 3 staff from CTU Prague had participated with duration: T.Dostál 15. – 18.12.2009 and J.Krása and T.Dvořáková 16. – 18.12.2009. Only allowances were covered from AKTION budget of BOKU Wien, while travel expenses were covered from another source.

There was saved from budget originally planned for CTU Prague (travel expenses for Czech staff and students to go to Vienna and accommodation and allowances of Austrian staff and students within the course in Prague) in total 17.400,- CZK, due to maximum discounts for train tickets and also out-season process were obtained for accommodation. These money were used at first to cover expenses related to issue of study materials (translation and small material for printing and also for presentation techniques. All purchased materials will be used also within courses, organized in next years.

All the invoices are stored at the economic department of CTU Prague. Regardless of relatively significant changes in project organization and general enlargement of the project`s goals, the expenses have not been reached totally.

Expenses of the Czech partner:

| Type of expenses: |  | CZK |
| --- | --- | --- |
| Accommodation of Austrian participants in the CR | Intensive course in the CR 29.11. – 3.12.2009, 15 persons, 4 nights | 28 000,- CZK |
|  | Accommodation - total | 28 000,- CZK |
| Daily allowances (meals) of Austrian participants in CR | Intensive course in the CR 29.11. – 3.12.2009, 17 persons, 5 days: Professor: 2x5x460,- = 4 600,- CZK Students: 15x5x250,- = 18 750,- CZK | 23 350,- CZK |
|  | Meals - total | 23 350,- CZK |
| Travel expenses of Czech participants to Austria | Common train ticket to Vienna -course 8. – 13.11.2009 (10+2 persons) - train | 12279,- CZK |
|  | Travel expenses - total | 12 279,- CZK |
| Material costs | Material | 9 371,- CZK |
|  | Translation | 8 000,- CZK |
|  | Material costs - total | 17 371,- CZK |
| Total | Costs - total | 81 000,- CZK |

Funds total available = funds used: 81 000,- CZK

Description of the expenses:

Accommodation of Austrian participants:

Accommodation has been provided in the service hostel of CTU Prague “Masarykova”, where following prices were finally offered (significantly lower, than was offered originally):

Masarykova:

560,- CZK/night in single room

435,- CZK/night.pers in double room

Two students of BOKU during their stay in Prague for the course overnight at their relatives or friends, therefore accommodation has not been necessary to charge for them and they were supplied only by allowances..

For professors accommodation in single rooms has been ordered automatically, for students double rooms were preferred. The total costs for accommodation of the students have been saved due to mainly lower prices, which were charged by CTU board. This procedure has been discussed in advance with Austrian partners as well.

Daily allowances for Austrian participants:

The allowances for students and professors had been supplied in full planned amount: 250,- CZK/pers.day for students and 460,- CZK/pers.day for professors.

Travel expenses of the Czech participants to Austria:

Travel expenses to Austria for spring intensive course have been paid by invoice for “collective train ticket”.

Material expenses:

As part of originally planned funds has been saved, it was used to cover material costs of the course. Professional translation of study texts were paid from this, small material (as papers, cartridges, etc. has been purchased, related to direct study material for the courses and presentation technique. All material will be used also within next courses, organized together by both participating institutions..

List of Czech participants at the course, held at BOKU Wienna

- Milena Hlaváčová

- Jana Hejná

- Barbora Janotová

- Michaela Klímová

- Kateřina Půstová

- Miroslav Bauer

- Iva Procházková

- Petr Šmejkal

- Luděk Strouhal

- Kateřina Lišková

Professors:

- Doc. Tomáš Dostál

- Ing. Tereza Dvořáková

List of Austrian participants at the course, held at CTU Prague

- Launay Marina

- Burzle Stefan Robert

- Hufler Stefan

- Nyamdavaa Tsolomon

- Kalss Rudolf

- Kyrnychnyj Andrey

- Lassing MArco

- Lebschy Markus

- Rummele Phillip

- Mullegger Matthias Stephan

- Seidl Georg

- Selim Shady

- Staudner Margarethe

- Baatar Naran Undrakh

- Muller Georg

Professors:

- Prof.Andreas Klik

- Ing. Gerlinde Trumper

In Prague, 28.1.2009

Assoc.Prof.Ing. Dr. Tomáš Dostál