Závěrečná zpráva o řešení projektu

AKTION 41p23

Přímé a nepřímé dopady erozních procesů – výzkum a modelování

(On- and Off- site effects of soil erosion processes – research and modelling).

za rok 2005

(vyúčtování za českou stranu)

Česká strana:

Katedra Hydromeliorací a krajinného inženýrství

Fakulta Stavební

ČVUT v Praze

zodpovědná osoba: Tomáš Dostál Ing., Dr.

Rakouská strana:

Institute of Hydraulics and Rural Water Management

University of Agricultural Sciences (BOKU) Wien

zodpovědná osoba: Andreas Klik Prof., Dipl.Ing. Dr.

Náplní projektu na rok 2005 byla jednak vzájemná návštěva spolupracujících týmů za účelem koordinace společně probíhajícího výzkumu a přípravy společných intenzivních výukových kurzů pro studenty obou univerzit a jednak intenzivní společné výukové kurzy pro studenty v délce trvání po 1 týdnu v Praze (ČVUT v Praze) a ve Vídni (BOKU Wien). Kromě toho proběhlo společné terénní měření na polním dešťovém simulátoru na experimentálních plochách v Rakousku.

V rámci projektu byly realizovány oba plánované intenzivní výukové kurzy v plánované délce, ale s mírnými úpravami v termínech konání a v počtu účastníků. Co se týče vzájemných návštěv členů řešitelských týmů, došlo k určitým úpravám, především v posunu termínů návštěv do podzimního období a  co do počtu pracovníků. Oproti původnímu plánu se podařilo ušetřit část finančních prostředků v CZK (podařilo se zajistit levnější jízdenky do Vídně a zpět v rámci konání kurzu a především se podařilo od vedení ČVUT v Praze získat poměrně výraznou slevu na ubytování, která původně nebyla kalkulována). Kromě toho byl snížen počet osob/den návštěv zaměstnanců z obou stran. Proto se mohlo terénního měření na dešťovém simulátoru účastnit více pracovníků (7 oproti plánovaným 4) a kurzu, pořádaného v Praze se tak mohlo účastnit více Rakouských studentů (celkem 21 oproti plánovaným 15). Prostředky byly operativně přesunuty k využití v rámci studijních kurzů, proto byla redukována jak návštěva Rakouských pracovníků v Praze na 2 osoby a 3 dny a návštěva pracovníků z Prahy na 3 dny a 5 pracovníků, přičemž pobytové náklady 2 z nich byly hrazeny z rozpočtu projektu pro rakouského partnera a 3 byli hrazeni ze zbývajících peněz české strany.

Podrobná specifikace aktivit následuje:

I. část kurzu proběhla pod názvem „Applied Methods of Soil Erosion Research“ v termínu 16. – 20.5.2005 ve Vídni s následujícím programem:

16.5.2005 – příjezd účastníků, přivítání, zahájení kurzu

17.5.2005 – všeobecné metodické přednášky a prezentace

18.5.2005 – modelování vodní eroze v laboratoři

19.5.2005 – modelování vodní eroze v laboratoři

20.5.2005 – závěrečné shrnutí, diskuze, ukončení kurzu, odjezd účastníků

Kurzu se zúčastnilo celkem 25 studentů a 4 učitelé – z toho za českou stranu 15 studentů a 2 učitelé (Dr.Ing. Tomáš Dostál a Ing. Hana Nováková) a za Rakousku stranu 10 studentů a 2 učitelé (Prof. Dr. Andreas Klik a Ing. Johanna Hoffmann)

II. část byla po společné dohodě posunuta na termín 21. – 25.11.2005 a byla organizována v Praze na Fakultě stavební ČVUT pod názvem „Soil Erosion and Sediment Transport, Measurement and Assessment“ s následujícím programem:

27.11.2005 – příjezd účastníků

28.11.2005 – úvodní přednášky, základy počítačového modelování

29.11.2005 – výpočet objemu sedimentu ve vodní nádrži s využitím GIS

30.11.2005 – odhad transportu sedimentu z povodí s využitím GIS

1.12.2005 – měření na laboratorním dešťovém simulátoru

2.12.2005 – závěrečná diskuze, závěry, shrnutí, odjezd účastníků

Kurzu se zúčastnilo celkem 31 studentů a 3 učitelé -  z toho za českou stranu 10 studentů a 3 učitelé (Dr.Ing. Tomáš Dostál a Ing. Hana Nováková) a za Rakousku stranu 21 studentů a 1 učitel (Prof. Dr. Andreas Klik). Počet Rakouských studentů byl navýšen díky mimořádnému zájmu o účast na kurzu za Rakouské strany. Rakouští studenti po dohodě obou partnerů byli seznámeni s tím, že z rozpočtu projektu bude plně uhrazeno jen jejich ubytování (do výše celkových schválených nákladů projektu), stravné a kapesné bylo po dohodě redukováno z plánovaných 250,-Kč na studenta a den na 245,- Kč na studenta a den. Prostředky byly získány jednak úsporou na ubytování a jednak redukcí počtu dnů, plánovaných na návštěvu rakouských kolegů v Praze z původních celkem 15 osoba/dny na 6 osoba/dny. Rakouské studenty během kurzu rovněž oproti plánu doprovázel jen jeden pedagog.

Oba kurzy na sebe navazovaly a zatímco kurz ve Vídni byl zaměřen na metody měření půdních charakteristik, kurz v Praze se zabýval využitím simulačních modelů pro posouzení erozní ohroženosti a návrh protierozních opatření. Kurz ve Vídni byl velmi kladně hodnocen jak pedagogy, tak především zúčastněnými studenty a velký zájem rakouských studentů o kurz v Praze svědčí o úspěchu této akce v loňském roce. Hodnocení kurzu několika studenty je přiloženo.

Na závěr každého z kurzů studenti dostali certifikáty o absolvování s uvedením, že se jednalo o kurz, organizovaný v rámci projektu AKTION 41P23. Vzorový certifikát je rovněž přiložen.

Plánovaná terénní simulace s dešťovým simulátorem proběhla v týdnu 5. – 9.9.2005 v Rakouském Mistelbachu na experimentálních plochách BOKU Wien. Z české strany se měření zúčastnilo celkem 7 osob, čímž byly vyčerpány i náklady plánované na návštěvu v laboratořích BOKU nicméně měrná kampaň byla natolik zajímavá a z odborného i praktického hlediska účelná a větší počet účastníků byl nezbytný pro zdárný průběh řešení, že účelu původně zamýšlené návštěvy bylo dosaženo.

Návštěva rakouských účastníků projektu  v Praze byla po dohodě vzhledem ke značné časové vytíženosti přesunuta až na začátek prosince 2005 a stejně jako reciproční návštěva českých pracovníků na BOKU Wien v polovině prosince 2005 byla zaměřena jednak na přípravu další spolupráce a jednak na přípravu společné publikace, využívající výsledků dosavadní spolupráce na dešťových simulátorech. Vzhledem k neudělení dalšího projektu v rámci programu AKTION byla rovněž snaha hledat další zdroje financování společných aktivit.

Veškeré účtování probíhalo na pracovišti fakulty stavební ČVUT v Praze odděleně a originály účetních dokladů jsou uloženy v ekonomickém oddělení řešitelského pracoviště. I přes určité změny v organizaci projektu oproti původnímu plánu -  a dá se říci – výraznému rozšíření aktivit, byly ve všech případech dodrženy jak maximální denní limity, tak i celková částka.

Vyúčtování nákladů za českou stranu:

| Typ nákladů |  | CZK |
| --- | --- | --- |
| Úhrada ubytování rakouských partnerů v ČR | Kurz v CR 27.11. – 2.12.2005: 22 osob, 5 nocí | 50 150,- CZK |
|  | Návštěva pracovníků BOKU 9. – 11.12.2005: 2 osoby, 2 noci | 1 500,- CZK |
|  | Ubytování celkem | 51 650,- CZK |
| Stravné Rakouských účastníků v ČR | Kurz v listopadu 27.11. – 2.12.2005: Profesoři: 1x5x380,- = 1 900,- CZK Studenti: 21x5x245,- = 25 725,- CZK | 27 625,- CZK |
|  | Návštěva pracovníků BOKU 9. – 11.12.2005: 2 osoby, 3 dny | 1 890,- CZK |
|  | Stravné celkem | 29 515,- CZK |
| Jízdné českých účastníků do Rakouska | Společná jízdenka na kurz 16. – 20.5. 2005 (15+2 osoby) - vlak | 17 164,- CZK |
|  | Cestovné 7 osob 5. – 9.9.2005 – polní dešťová simulace (auto) | 8 570,- CZK |
|  | Cestovné 5 osob 14. – 16.12.2005 – návštěva pracovníků ČVUT (auto) | 4 189,- CZK |
|  | Jízdné celkem | 29 923 CZK |
| Pobytové náklady a náklady na ubytování českých účastníků při návštěvě v Rakousku | Cestovní náklady pracovníků ČVUT (3 osoby podle zásad ČR) 14. – 16.12.2005 | 26 086,- CZK |
|  | Pobytové náklady v Rakousku celkem | 26 086,- CZK |
|  | Náklady celkem | 137 174,- CZK |

K realizaci projektu přiděleno celkem: 138 000,- CZK

Zbylé prostředky ve výši 826,- CZK byly využity v rámci nákupu odborné literatury pro knihovnu řešitelského pracoviště

Zdůvodnění nákladů:

Ubytování Rakouských účastníků:

Ubytování účastníků bylo zajištěno v režijních zařízeních ČVUT Krystal a Masarykova kolej, kde byly přiznány režijní ceny ve výši:

Krystal:

630,- CZK/os.noc ve jednolůžkovém pokoji

415,- CZK/os.noc ve dvoulůžkovém pokoji

Masarykova kolej:

375,- CZK/os.noc ve dvoulůžkovém pokoji

Účastníci kurzu byly z kapacitních důvodů ubytováni v hotelu Krystal, návštěva pracovníků BOKU v prosinci 2005 pak na Masarykově koleji.

Profesorům bylo zajištěno automaticky ubytování na jednolůžkových pokojích, studenti pak byli rozděleni podle kapacity převážně do dvoulůžkových pokojů. Celková částka na ubytování včetně pokrytí vyššího počtu studentů navýšení počtu studentů – účastníků kurzu o 6 osob, byla získána především díky zajištění levnějšího ubytování a dále pak z limitu na ubytování pedagogů v délce 5 dnů, který byl redukován na 2 osoby na tři dny. Tento postup byl konzultován se zástupci DZS v Praze a s rakouskými partnery.

Stravné rakouských účastníků:

Stravné rakouského profesora v rámci kurzu bylo vyplaceno přesně v souladu s plánem. Stravné pro studenty – účastníky kurzu bylo kráceno z plánovaných 250,- Kč/os.den na 245,- Kč/os.den na základě předběžného projednání se zástupci DZS v Praze a rakouskými partnery. Chybějící náklady na stravné byly pokryty využitím plánovaných financí na stravné pro 3 zaměstnance BOKU v rámci jejich 5-ti denního pobytu na ČVUT v Praze, který byl redukován na  2 osoby na tři dny a dále díky levnějšímu zajištěnému ubytování.

Jízdné českých účastníků do Rakouska:

Jízdné na kurz bylo hrazeno fakturou za hromadnou jízdenku na vlak. Na výjezd za účelem polní dešťové simulace byly vzhledem k vyššímu počtu účastníků (7 osob) a rovněž tak vzhledem k odlehlé lokalitě, využity dva osobní automobily. Stejně tak na závěrečné jednání ve Vídni v prosinci 2005 byl využit osobní automobil.

Pobytové náklady českých účastníků v Rakousku:

Závěrečného jednání se zúčastnilo z české strany celkem 5 osob/tři dny – pobytové náklady dvou z nich byly z větší části hrazeny z rakouské strany, zbytek jejich nákladů a plná úhrada za zbylé tři osoby/tři dny byla provedena z prostředků uspořených především díky levnějšímu ubytování rakouských účastníků i zaměstnanců v Praze.

V Praze dne 20.1.2006

Ing.Dr.Tomáš Dostál

Final report on the project

AKTION 41P23

On- and Off- site effects of soil erosion processes – research and modelling

for 2005 year

(overview of the costs for Czech partner)

Czech partner:

Department of Drainage Irrigation and Landscape Engineering

Faculty of Civil Engineering

CTU in Prague

Tomáš Dostál Ing., Dr.

Austrian partner:

Institute of Hydraulics and Rural Water Management

University of Agricultural Sciences (BOKU) Wien

Andreas Klik Prof., Dipl.Ing. Dr.

The topic of the project for 2005 had been at first exchange visit of both teams, to coordinate ongoing research projects, cooperation and to prepare the intensive student courses with duration one week each (at CTU Prague and at BOKU Wien) and at second, intensive common student courses itselves. Additionally, common field experiments with field rainfall simulator were organized on experimental plots in Austria.

Within the project, both planned courses were realized in planned duration, but with minor changes, concerning of the term and number of participants, which had been increased for the course held in the Czech Republic. Concerning of the staff visits also some partial changes had been adopted, mainly in number of participants and term. The organizers succeeded and saved part of the money, mainly due to they have got a significant credit for accommodation prices in Prague, in compare with originally announced ones and also higher reduction, that was announced was obtained for train tickets to intensive course in Vienna. In addition, there was lowered the number of person/days, planed for staff exchange from both sides. Due to this fact, the number of Austrian participants of the course could been increased significantly (21 students to 15 planned) as well as the number of the Czech participants of field rainfall experiments in Austria (7 staff to 4 planned). The funds were operatively shifted to support student course in Prague also, because of the reduction of person/days of Austrian staff in Prague (only 2 persons/3 days) and also as for visit of the Czech staff in Vienna (5 staff/3 days), 2 persons were covered from Austrian budget and 3 persons were covered from Czech part of the budget.

The detailed specification of the activities and costs follows:

I. part of the course had been held at BOKU Wien under the title “Applied Methods of Soil Erosion Research “during 16. – 20.5.2005  with following program:

16.5.2005 – arrival of the participants, welcome, introduction

17.5.2005 – general methodological presentations and lectures

18.5.2005 – modeling of erosion processes in soil laboratory

19.5.2005 – modeling of erosion processes in soil laboratory

20.5.2005 – final discussion, conclusion, finishing of the course, departure of the participants

There were in total 25 students and 4 teachers participating at the course – from the Czech Republic 15 students and 2 teachers (Dr.Ing. Tomáš Dostál a Ing. Hana Nováková) and from Austria 10 students and 2 teachers (Prof. Dr. Andreas Klik a Ing. Johanna Hoffmann)

II. part of the course at CTU in Prague under the title „Soil Erosion and Sediment Transport, Measurement and Assessment“ had been planed  after common agreement to 27.11. – 2.12.2005  with following program:

27.11.2005 – arrival of the participants

28.11.2005 – introduction to computer modeling

29.11.2005 – sediment volume in the water reservoir assessment using GIS technology

30.11.2005 – sediment transport from the watershed assessment, using GIS technology

1.12.2005 – measurement on the laboratory rainfall simulator

2.12.2005 – final discussion,, conclusions, finishing of the course, departure of the participants

There were in total 31 students participating at the course and 4 teachers – 10 students and 3 teachers (Dr.Ing. Tomáš Dostál, Ing. Josef Krása Ph.D. and Ing. Hana Nováková) from the Czech Republic and 21 students and 1 teacher from Austria (Prof. Dr. Andreas Klik). The number of Austrian students has been increased, due to very high interest at BOKU to take a part at the course. There had been agreed, that Austrian students will have covered from the budget of the project the only expenses for accommodation and partly for traveling – up to total project costs, daily allowances in the Czech Republic will be covered by the project only till the financial limit of the project – students day limit has been decreased to 245,- CZK from originally planned 250,- CZK. The rest of the costs will be covered by the students themselves. The extra expenses were covered from saved funds due to cheaper accommodation, reduction of staff person/days and also due to the only one teacher from Austrian partner took a part at the course.

Both courses have followed each other thematically – as the course in Wien had been focused of laboratory and field measurement techniques of sol erosion processes, the Prague course was oriented more on the computer modeling and practical implementation of GIS technology. The course in Vienna had been highly appreciated by teachers, but mainly by students and high interest of the students for the Prague course had shown good image of the course organized last year. The evaluation of the course in Vienna by several CTU students is enclosed.

At the end of common courses the participants obtained certificates, which approved, that students passed intensive course, held under AKTION project 41P23. The sample of the certificate is also enclosed.

Planned field simulation with rainfall simulator went on during the 5. – 9.9.2005 in Austrian Mistelbach, where experimental plots of BOKU are located. From Czech side, in total 7 participants took a part, as there was necessary to gather more people for field works, which spent all planned money for visits of Czech partners at BOKU. But the field campaign has been so interesting and fruitful from point of view of practical and expert point of view, that all goals of planed visit had been reached.

Visit of Austrian partners at CTU Prague has been shifted after common agreement and due to extreme lack of time to beginning of December, the same as final visit of Czech partners in Vienna to mid of December. The visits were focused mainly to discussion, of the assessment of the results of common experiments on rainfall simulator – both of field from summer 2005 at Mistelbach and laboratory ones, done separatelly in labs in Prague and in Vienna. Also new ways of cooperation financing were searched for, as new AKTION project for 2006 has been rejected.

All the invoices are stored at the economic department of CTU Prague. Regardless of relatively significant changes in project organization and general enlargement of the project`s goals, the expenses have not been reached totally.

Expenses of the Czech partner:

| Type of expenses: |  | CZK |
| --- | --- | --- |
| Accommodation of Austrian participants in the CR | Intensive course in the CR 27.11 – 2.12.2005, 22 persons, 5 nights | 50 150,- CZK |
|  | Visit of BOKU staff 9. – 11.12.2005; 2 persons, 2 nights | 1 500,- CZK |
|  | Accommodation - total | 51 650,- CZK |
| Daily allowances (meals) of Austrian participants in CR | Intensive course in the CR 27.11 – 2.12.2005, 22 persons, 5 days: Professor: 1x5x380,- = 1 900,- CZK Students: 21x5x245,- = 25 725,- CZK | 27 625,- CZK |
|  | Visit of BOKU staff 9. – 11.12.2005; 2 persons, 3 days | 1 890,- CZK |
|  | Meals - total | 29 515,- CZK |
| Travel expenses of Czech participants to Austria | Common train ticket to Vienna -course 16. – 20.5.2005 (15+2 persons) - train | 17 164,- CZK |
|  | Travel expenses – field simulation 5. – 9.9.2005 (7 persons = 2 cars) | 8 570,- CZK |
|  | Travel expenses CTU staff 14. – 16.12.2005 - 5 persons in December (car) | 4 189,- CZK |
|  | Travel expenses - total | 29 923,- CZK |
| Daily allowances and accommodation of Czech staff in Austria | Daily allowances and accommodation for visit BOKU 14. – 16.12.2005, according to Czech standards | 26 086,- CZK |
|  | Daily allowances and sccommodation | 26 086,- CZK |
| Total | Costs - total | 137 174,- CZK |

Funds total available: 138 000,- CZK

Funds extra (total 826,- CZK) have been gathered to buy special literature from the field of soil erosion and sediment transport research for the library of CTU Prague.

Description of the expenses:

Accommodation of Austrian participants:

Accommodation has been provided in the service hostels of CTU Prague “Krystal” and “Masarykova”, where following prices were finally offered (signifficantly lower, than was offered originally):

Krystal:

630,- CZK/night in single room

415,- CZK/night in double room

Masarykova:

375,- CZK/night in double room

The participants of the course have been (because of capacity reasons) accommodated in Krystal hotel, while staff in December stayed in Masarykova.

For professors accommodation in single rooms has been ordered automatically, for students double rooms were preferred. The total costs for accommodation of the students have been have been saved due to mainly lower prices, which were charged by CTU board. And also because of reduction of staff exchange activities from both sides. This procedure has been discussed in advance with AKTION office in Prague and with Austrian partners as well.

Daily allowances for Austrian participants:

Daily allowances of Austrian professors have been paid fully according to limits. The allowances for students within the course has been lowered, according to common agreement, from 250,- CZK to 245,- CZK/pers.day in agreement with prelilminar discussion with AKTION office in Prague and also with Austrian partner. Still missing funds have been filled from the allowances, planned for visit of 3 staff for 5 days, which has been reduced only to 2 persons/3 days and also from saved money from accommodation of Austrian students.

Travel expenses of the Czech participants to Austria:

Travel expenses to Austria for spring intensive course have been paid by invoice for “collective train ticket”. The travel costs to field rainfall simulation cover car expenses, because of higher efficiency of this transport and also troubles with reaching the locality by public transport. For winter visit, personal cars have been used, respecting planed expenses and to save both of time and money.

Daily allowances and accommodation of CTU staff in Vienna:

Final meeting of the project was held in December 2005 in Vienna and sta costs were paid by gathering of the funds left on both sides. Therefore, 2 people were paid mostly by Austrian side, while stay of three people was covered fully by  ty funds of the Czech partner.

In Prague, 20.1.2006

Ing. Dr. Tomáš Dostál