Final report on the project AKTION 41P22

“Soil Erosion and Sediment Transport Processes Research and Modeling”

for 2006 year

Czech partner:

Department of Drainage Irrigation and Landscape Engineering

Faculty of Civil Engineering

CTU in Prague

Tomáš Dostál Ing., Dr.

Austrian partner:

Institute of Hydraulics and Rural Water Management

University of Agricultural Sciences (BOKU) Wien

Andreas Klik Prof., Dipl.Ing. Dr.

The topic of the project for 2005 had been at first exchange visit of both teams, to coordinate ongoing research projects, cooperation and to prepare the intensive student courses with duration one week each (at CTU Prague and at BOKU Wien) and at second, intensive common student courses itselves. Further cooperation within 7th Frame Program of EU has been discussed during visits of staff in December 2006.

Within the project, both planned courses were realized in planned duration and terms, just with increase of number of participants at both sides, without increasing of planned costs. Concerning of the staff visits also some partial changes had been adopted, mainly in terms of the visits. The organizers succeeded and saved part of the money, mainly due to they have got a significant credit for accommodation prices in Prague, in compare with originally announced ones and also higher reduction, that was announced was obtained for train tickets to intensive course in Vienna. Due to this fact, the number of Austrian participants of the course could been increased significantly (20 students to 15 planned) as well as the number of the Czech students at the course in Vienna (12 to 10 planned).

The detailed specification of the activities and costs follows:

I. part of the course had been held at BOKU Wien under the title “The research and modeling of soil erosion and transport processes“ during 1. – 6.10.2006  with following program:

1.10.2006 – arrival of the participants, welcome

2.10.2006 – introduction, general methodological presentations and lectures

3.10.2006 – modeling of erosion processes in soil laboratory

4.10.2006 – modeling of erosion processes in soil laboratory

5.10.2006 – calculation of measured results, statistical evaluation of measured data

1.10.2006 - final discussion, conclusion, finishing of the course, departure of the participants

There were in total 17 students and 4 teachers participating at the course – from the Czech Republic 12 students and 2 teachers (Dr.Ing. Tomáš Dostál a Ing. Hana Nováková) and from Austria 5 students and 2 teachers (Prof. Dr. Andreas Klik a Ing. Nicole Emmerstorfer). Number of Czech students has been increased from 10 to 12 due to simpler and therefore cheaper accommodation, provided by Austrian colleagues and also by higher financial participation of the students.

II. part of the course at CTU in Prague under the title „ The research and modeling of soil erosion and transport processes “ had been held  on 26.11. – 1.12.2006  with following program:

26.11.2006 – arrival of the participants

27.11.2006 – introduction to computer modeling

28.11.2006 – sediment volume in the water reservoir assessment using GIS technology

29.11.2006 – sediment transport from the watershed assessment, using GIS technology

30.11.2006 - measurement on the laboratory rainfall simulator

1.12.2006 – final discussion,, conclusions, finishing of the course, departure of the participants

There were in total 28 students participating at the course and 4 teachers – 10 students and 2 teachers (Dr.Ing. Tomáš Dostál, Ing. Josef Krása Ph.D.) from the Czech Republic and 20 students and 2 teachers from Austria (Prof. Dr. Andreas Klik, Ing.Nicole Emerstorfer). The number of Austrian students has been increased, due to very high interest at BOKU to take a part at the course. There had been agreed, that Austrian students will have covered from the budget of the project the only expenses for accommodation and partly for traveling – up to total project costs, daily allowances in the Czech Republic will be covered by the project only till the financial limit of the project – students day limit has been decreased to 230,- CZK from originally planned 250,- CZK, daily allowances for professors were also reduced from 380,- to 360,- CZK. The rest of the costs was covered by the students themselves. The extra expenses were covered from saved funds due to cheaper accommodation and cheaper transportation of Czech students to Vienna.

Both courses have followed each other thematically – as the course in Wien had been focused of laboratory and field measurement techniques of sol erosion processes, the Prague course was oriented more on the computer modeling and practical implementation of GIS technology. The course in Vienna had been highly appreciated by teachers, but mainly by students and high interest of the students for the Prague course had shown good image of the course organized last year. The evaluation of the course in Vienna by several CTU students is enclosed.

At the end of common courses the participants obtained certificates, which approved, that students passed intensive course, held under AKTION project 45Pp22. The sample of the certificate is also enclosed.

Visit of Austrian partners at CTU Prague has been shifted after common agreement and due to extreme lack of time to beginning of December, the same as final visit of Czech partners in Vienna to mid of December. The visits were focused mainly to discussion, of the assessment of the results of common experiments on rainfall simulator, done separately in labs in Prague and in Vienna and also to future cooperation within the project of 7th Frame Program of EU.

All the invoices are stored at the economic department of CTU Prague. Regardless of relatively significant changes in project organization and general enlargement of the project`s goals, the expenses have not been reached totally.

In Prague, 17.1.2007

Ing. Dr. Tomáš Dostál